Agenda with notes:

* Procurement/availability of sampling materials:
  + scale books & Whatmans from RCH broodstock project (all at RCH),
  + data sheets (Nick Bohlender will bring),
  + knives,
  + metal spoon (at RCH),
  + buckets or bags to transport eggs (all at RCH),
  + electronic scale (RCH),
  + fish tags (Nick has leftover from last year),
  + juvenile measuring board (RCH)
* Ratification of staffing schedule
  + Dates for spawnings to be relayed by Steve toward the end of the preceding week.
  + Egg takes will start around 10AM.
  + Nick Brown to text Jeff Till and make sure he’s still available
* Any as-yet unaddressed considerations from RCH staff
  + Steve wondering which table was used in Incubation for the egg sampling/measuring. Folding plastic table used at Conuma last year.

Schedule:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Week | Day 1  (11 October) | Day 2 | Day 3 | Sample target | Comments |
| 9-13 October | Nick Bohlender, Jeff T, Aidan | Nick Bohlender, Aidan, Piper | Jeff T, Piper, Nick B(?) | 60-70 | Nick (& Aidan) go to RCH on 10 October to set up and liaise with hatchery crew. Can stay overnight at the bunkhouse if they wish. |
| 16-20 October | Aidan, Christie, TBD | Piper, Kiran | Piper, Christie | 60 |  |
| 23-27 October | Aidan/Piper, TBD | Piper/Aidan, TBD |  | 40 | May involve only 1-2 days of light sampling |